## Demo Comments
Day / Comments / Attendees' | Remarks | Status
12th May 2022 Demo Comments - Ulag & Kesavan |  | 1 + 2
All Earlier remarks to be displayed. | Updated | Closed
Excel File name to have project (SK Number) and Jobname | Updated | Closed
Severity to be entered by PM based on model only. | Updated | Closed
Additional column to be added during back draft stage for capturing model update. | Updated | Closed
Control for completed will be done based on model update only. if pending record's cant be moved to next stage. | Updated | Closed
3 Documents [log, register, merged] - one drawing and one model register for one project. | Later [Next Release] | Open
13th May 2022 Demo Comments - Vishwa, Ulag, Kesavan, Nimain & Sathish |  | 1 + 5
Agreed only - Model updated will be enabled else disabled | Control not feasible in UI hence records won’t be moved to next process unless all points are closed. | Closed
If disagree then remarks is mandatory | Function added when disagree remarks should be there else wont move to next process | Closed
validation of model updated based on agree condition to be done before completed or move to next stage | Function added when disagree remarks should be there else wont move to next process | Closed
Report Number will be based on project, SK1741-001(three digits)-ABM Checking, ..... | Updated | Closed
Sequence number will be based on guid part phase name | Updated | Closed
modeller will be the owner who will be adding the guid into the system. | Updated | Closed
back check agree and one more column back check observation to be added | Updated | Closed
before qa stage DPM will have full control where he can change the stage. | Before stage alone allowed | Closed
old report or new report before rolling out on or before 18th May 2022 | Updated | Closed
Excel File name to have unique report number | Updated | Closed
guid deleted will be shown as red in user interface (Row will be red font) | Updated | Closed
23rd May 2022 Demo Comments - Vishwa, Ulag, Kesavan, Nimain & Sathish |  | 1 + 5
Demo - Ulag as Modeller, Vijay as Checker & Vishwa as PM (Dummy Project : SK1741, Report : 017-Seq01) | Testing Done - No issues in functionality
Single sign on "SKS%%%" windows login will be used. - MD | Updated | Closed
Tools will run only for "esskaystructure" domain users - MD | Updated | Closed
File name will have ";" with space between two report number - BNS | Updated | Closed
Approved by to be done based on Severity entry user - PVK | Updated | Closed
Seq01 - after moving from back draft still showing in dash board (tree view) - Ulag | Updated | Closed
Forms Size to be increased with all font height as 11 - BNS | Updated | Closed
Wrap text to be done with fixed column width - Kesavan / BNS | Updated | Closed
Back check observation record will be considered as checker observation - BNS. | Updated | Closed
Earlier entry will be in database for getting the history - Kesavan / BNS. | Updated | Closed
Use Capitals letter for "OK" or two letter words for more length words will begin with start letter capital - BNS | Updated | Closed